## TODO
Feature | Needs | Timeframe | Priority | Done | Notes
Day panel |  |  | 0 | Done
Day panel max scale |  |  | 1.1 | Done | Make max scale proportional to viewport, if scale less than viewport, scale to viewport, then expand to week view, IsMaxScale
Day panel horizontal |  |  |  | Done | Mark everything that involves dimensions, Mark everything that is only 1D. Then draw the rest of the fucking owl
Cal Panels Orientation |  |  |  | Done
Cal Panels IScrollInfo |  |  |  | Done |  | 64 | 5.8182
Date watermark |  |  |  | Done |  | 129 | 11.7273
TextMargin toggle |  |  |  | Done
Improve TextMargin cutoffs |  |  |  | Done
Day panel cursor |  |  |  | Done | An animated glowy rgb line that continuously updates to follow DateTime.Now. Animates smoothly over 1 second, updated once per second
DayView |  |  | 0.7 | Done | Buttons back forward 1 date, viewmodel of TimeTasks, transform them into CalObjs, bind Day itemsource to CalObjs
Week panel | day panel |  | 4 | Done | Identical to a Day panel, but has start and end dates for the beginning and end of the week that Date is in. Date is highlighted.
VerticalLRWeekView | Week panel |  |  | Done | This is a horizontal list of vertical days. Week.Width is fixed to VP width. Scale and Offset affects all days at once.
HorizontalUDWeekView | VerticalLRWeekView |  |  | Done | This is a vertical list of horizontal days. Week.Height is fixed to VP Height.
WeekView |  | 3 | 5 | Done | Horizontal list of Day panels, bind first day panel itemssource to calobjs
MonthView | week view | 3 | 8 | Done
Day not in month styles |  |  |  | Done | flag, gray background, darker gray watermark, distinguishable from month days
Calendar views |  | 3 | 10 | Done
Double click week to WeekView |  |  |  | Done
CalendarPicker |  |  |  | Done | Use the DatePicker to choose a date
Swap Calendar Views |  |  |  | Done | Figure out how to easily swap to month/week/day views
CalendarViewModel |  | 3 | 2 | Done
DayViewModel | CalendarViewModel | 3 | 3 | Done |  |  | Kill spaces | ^\s*$\n
WeekViewModel |  | 3 | 7 | Done
MonthViewModel |  | 3 | 9 | Done
CalendarObject control |  | 3 | 11 | Done | Finish properties. Different types? There are tasks that can be completed and pushed, but there are immutables like holidays. Different dimension for holidays. Dimensions signify layers when drawn. Objs of diff dimensions can be simultaneous. Objs can filter by label even if label is in another dimension.
Draw objects on Calendar | task events |  | 12 | Done
Notes show up on calendar |  |  |  | Done
Implmnt TimeTasks on Calendar
build task events | cal views, better PatternView |  | 13
states | Draw objects on Calendar | 6 | 18 |  | trigger states based on timertick event
checkins | states | 6 | 19 |  | Create new Note at current time with task type set to 'checkin', edit popup for task under nowmarker, edit for state
click a CalendarObject |  | 3 | 16 |  | CalObj creates event. VM listens for event. Register even when creating in VM before adding to collection.
Collisions | states | 6 | 15 |  | "We found a conflicting object at 4:45PM, what do you want to do?" Push, Merge, Yield, Edit, Cancel
Selector |  | 3 | 17 | Done | using ListBox
better pattern view |  | 6 | 14
Draw concurrent CalendarObjects
Note types graphic | concurrent CalObjs |  |  |  | Draw notes with a little note graphic on the right side of a day
better timespan picker |  | 2 | 20 |  | separate spinners for year month day time
Data Analysis of Notes |  | 4 | 21
Data Analysis of Calendar | states | 4 | 22
priority view | states | 4 | 23
task suggestions | priority view | 6 | 24
Validate input | states |  |  |  | Validate input by coloring the date entered box according to the state of the calendar object occupying that time if there is one
Suggest input | validate input
resources view | states | 4 | 25
local file DB |  |  |  | Done
Remote Desktop Tight VNC |  | 1 | 26
powerpoint Presentation | 3+ assessments, local db | 10 | 27 |  | MainWindowVM -> Navigate -> GetDataCmd ->
Filters |  | 6 | 28
themes |  | 1 | 29
graphs | data analysis | 20 | 30
Day panel UI Virtualization |  | 4 | 31 | no need? | ListBox already does virtualization?
Continuous Day Panel |  |  | 31.1 |  | Identical to a Day panel, but not restricted to a single day, update Date and watermark to date with most area, when midnight passes viewport middle. Update extent range to 3 days before, current, after
HorizontalLRWeekView | continuous day panel |  | 31.2 |  | Hoizontal week, horizontal days. This will just use a horizontal ContinuousDay panel
VerticalUDWeekView | continuous day panel |  | 31.3 |  | Vertical week, vertical days. This will just use a vertical ContinuousDay panel
Animate watermark | continuous day panel | 1 | 32 |  | When scrolling to next day, animate the watermark to follow midnight. Offset is a max calculation between viewport top, bottom, day top, bottom
Stacking calendar objects |  | 4 | 33 |  | Smartly fit them like legos. They have to be different dimensions. Fit in measure/arrange
Ruler teeth style |  | 4 | 34
Clock |  |  |  | Done
VM only change tracking |  |  |  |  | Could be achieved by not putting CollectionView in edit mode when VM is in edit mode, but if view is editing when trying to commit, cancel view edit, then commit
Day TODOs |  |  |  |  | search TODO
What is WCF and why should I care?
SCM issue tracking
Agile Scrum
CalendarObject thumbs
YearView |  |  |  |  | Like MonthView, a ListBox of months, select month, double click month to MonthView
Pages
Autocomplete textboxes
Color by type/state
New Note Here |  |  |  |  | Set time to where cursor is on day/week panel
CalendarVM works like NotesVM
Legend
SQL Server CE
Label hits |  |  |  |  | sort labels by hits. Score hits by uses.
CalendarObject selected |  |  |  |  | store selected state in CalendarObject so that selection box can be propogated through mimicry
On Commit |  |  |  |  | Prevent any operations while commiting
week view save as |  |  |  |  | save image and txt

## Sheet1
Main purposes of this program:
To ultimately decide on the best use of my time at any given time, based on allocation of priorities based on my values
To help me discover what my values are, based on trends of how time was spent, how I felt during that time, and my opinion of that time in retrospect