## Sheet1
Feature | Needs | Timeframe | Priority | Done | Notes
Day panel |  |  | 0 | Done
Day panel max scale |  | 2h | 1.1 | Done | Make max scale proportional to viewport, if scale less than viewport, scale to viewport, then expand to week view, IsMaxScale
Day panel horizontal |  |  |  | Skip
CalendarObject control |  | 3h | 0.7
WeekView |  | 3h | 0.8 |  | Horizontal list of Day panels
week zooming | Day horizontal, max scale |  |  |  | With horizontal Days at max scale, scaling should already happen by just shrinking week grid, nothing to code
MonthView |  | 3h | 0.9
Calendar views |  | 1d | 1
Draw objects on Calendar | task events | 1d | 2 |  |  | Kill spaces | ^\s*$\n
build task events | cal views, better PatternView | 1d | 3
better pattern view |  | 1d | 4
Collisions | states | 6h | 5
states | Draw objects on Calendar | 2h | 6
checkins | states | 2h | 7
better timespan picker |  | 2h | 8
Data Analysis of Notes |  | 2h | 9
Data Analysis of Calendar | states | 4h | 9
priority view | states | 4h | 10
task suggestions | priority view | 4h | 11
resources view | states | 4 hours | 12
local file DB |  | 30m | 13
Remote Desktop Tight VNC |  | 1h | 13
powerpoint Presentation | 3+ assessments, local db | 4h | 14
Filters |  | 6h | 15
themes |  | 2h | 16
graphs | data analysis | 2d | 17
VM only change tracking |  |  |  |  | Could be achieved by not putting CollectionView in edit mode when VM is in edit mode, but if view is editing when trying to commit, cancel view edit, then commit
Assessment | breakthrough
Clock |  | 30m
Cal Panels Orientation |  | 4h
Cal Panels IScrollInfo |  | 6h