## Sheet1
Feature | Needs | Timeframe | Priority | Done | Notes
Day panel |  |  | 0 | Done
Day panel max scale |  | 2h | 1.1 | Done | Make max scale proportional to viewport, if scale less than viewport, scale to viewport, then expand to week view, IsMaxScale
Day panel horizontal |  |  |  | Done | Mark everything that involves dimensions, Mark everything that is only 1D. Then draw the rest of the fucking owl
Cal Panels Orientation |  | 4h |  | Done
Cal Panels IScrollInfo |  | 6h |  | Done
Date watermark |  |  |  | Done
TextMargin toggle |  |  |  | Done
Improve TextMargin cutoffs |  |  |  | Done
DayView |  |  | 0.7 |  | Buttons back forward 1 date, viewmodel of TimeTasks, transform them into CalObjs, bind Day itemsource to CalObjs
Day panel cursor |  |  |  | Done | An animated glowy rgb line that continuously updates to follow DateTime.Now. Animates smoothly over 1 second, updated once per second
Week panel | day panel |  | 0.77 |  | Identical to a Day panel, but has start and end dates for the beginning and end of the week that Date is in. Date is highlighted.
WeekView | week panel | 3h | 0.8 |  | Horizontal list of Day panels, bind first day panel itemssource to calobjs
week zooming | Day horizontal, max scale weekk panel |  | 0.85 |  | With horizontal Days at max scale, scaling should already happen by just shrinking week grid, nothing to code
MonthView | week view | 3h | 0.9
Calendar views |  | 1d | 1 |  |  | Kill spaces | ^\s*$\n
CalendarObject control |  | 3h | 1.1 |  | Finish properties. Different types? There are tasks that can be completed and pushed, but there are immutables like holidays. Different dimension for holidays. Dimensions signify layers when drawn. Objs of diff dimensions can be simultaneous. Objs can filter by label even if label is in another dimension.
Draw objects on Calendar | task events | 1d | 2 | Done
build task events | cal views, better PatternView | 1d | 3
better pattern view |  | 1d | 4
Collisions | states | 6h | 5
states | Draw objects on Calendar | 2h | 6
checkins | states | 2h | 7
better timespan picker |  | 2h | 8 |  | separate spinners for year month day time
Data Analysis of Notes |  | 2h | 9
Data Analysis of Calendar | states | 4h | 9
priority view | states | 4h | 10
task suggestions | priority view | 4h | 11
resources view | states | 4 hours | 12
local file DB |  | 30m | 13
Remote Desktop Tight VNC |  | 1h | 13
powerpoint Presentation | 3+ assessments, local db | 4h | 14
Filters |  | 6h | 15
themes |  | 2h | 16
graphs | data analysis | 2d | 17
VM only change tracking |  |  |  |  | Could be achieved by not putting CollectionView in edit mode when VM is in edit mode, but if view is editing when trying to commit, cancel view edit, then commit
Assessment | breakthrough
Clock |  | 30m
Validate input | states |  |  |  | Validate input by coloring the date entered box according to the state of the calendar object occupying that time if there is one
Suggest input | validate input
Continuous Day Panel |  |  |  |  | Identical to a Day panel, but not restricted to a single day, update Date and watermark to date with most area, when midnight passes viewport middle. Update extent range to 3 days before, current, after
Animate watermark |  |  |  |  | When scrolling to next day, animate the watermark to follow midnight. Offset is a max calculation between viewport top, bottom, day top, bottom
Stacking calendar objects |  |  |  |  | Smartly fit them like legos. They have to be different dimensions. Fit in measure/arrange
Day TODOs |  |  |  |  | search TODO
What is WCF and why should I care?
ADO.NET
Ruler teeth style